## Slide 1: Procurement Process

## Slide 2: Outline
Planning
Bidding process
Contract Management

## Slide 3: What is procurement process
System of procedures on how procurement should be done

## Slide 4: Procurement cycle

## Slide 5: Planning
The public entity must plan each step of the procurement process and prepare annual procurement plan (sec. 25 (4)(a))

## Slide 6: Planning
Identifications of need
Public Entity must determine whether a need exist and how best to fulfil the need
The identification of the need is done by the User Department

## Slide 7: Planning
To be taken the following into consideration:
  Assessment of the need to procure
  Conducting of market research and cost estimate
  Identification of source of fund
  Defining and describing the requirements
  Selection of appropriate procurement method
  Selection of contract approach and structure, etc.

## Slide 8: Planning
Formulate the Entity Annual procurement plan (3 months before the new financial year)
Approved by the accounting officer
Submit to policy unit
Implementation start thereof.

## Slide 9: Bidding Documents
Purpose of bidding documents – (Sec. 43 & Reg. 33)
  To provide to bidders with the information that they require to prepare and submit bids in a timely and proper manner and that are responsive to the requirements of the public entity
  Good bidding documents are a pillar of successful procurement proceedings

## Slide 10: Bidding Documents
Contents of bidding documents is to provide to bidders:
  Procedures and forms for preparation and submission of bids
  Technical description of object of procurement
  Qualification criteria
  Technical evaluation criteria
  Contract terms and conditions
Issue of Bidding documents
  To all bidders who respond to invitation or to all pre-qualified bidders

## Slide 11: Invitation for Bidding
Invite bidders to submit priced offers as per Public Entities requirements
Must be done in a widely circulated newspaper for competitive bidding method
Where pre-qualifications was done, the document is only issued to bidders who have been pre-qualified.

## Slide 12: Bid Securing Declaration
"A bid securing declaration is an alternative to Bid Security where there is no financial security offered. The bidder declare that they can be disqualified/suspended failure to comply with section 45 of act

## Slide 13: Execution of Bid Securing Declaration
In terms of section 45 bidder accept disqualified/suspended in the event of:
  a modification or withdrawal of a bid after the deadline for submission of bids during its period of validity;
  refusal by a bidder to accept a correction of an error appearing on the face of the bid;
  failure by a successful bidder to sign a procurement contract in accordance with the terms set forth in the bidding documents
  failure by a successful bidder to provide security for the performance of the procurement contract if required to do so by the bidding documents

## Slide 14: Bid validity period
Valid for the period indicated in the bidding documents (Sec. 49)
Any deviation from this period is considered a major deviation
Period must be set in relation to the time required to evaluate and approve a procurement activity
The validity period may be extended but may not go over 180 days (six month), but must be extended before it expires

## Slide 15: Clarifications
Bidders may request a public entity to give clarifications on content of bidding documents (Reg. 34)
Request for clarifications should be in writing and submitted before deadline set for seeking clarifications
  Procurement involving competition: 14days prior to deadline
  Procurement not involving competition: 7days prior
Public entity should respond within 3days of receipt of request and share the clarifications with all other bidders without disclosing the identity of the bidder making the request
Modifications if required should be made to the bidding documents going forward

## Slide 16: Deadline for submission of bids
Sufficient time should be allowed for bidders to respond, depending on the complexity of the procurement (Sec. 47)
Bids received after the deadline shall be returned unopened to the bidder
For invitation to bid, the deadline for submission may not be less then 31 working days from date of publication of invitation (Reg. 35 as amended)

## Slide 17: Submission of bids
Submitted in writing, duly signed and in a sealed envelope at the address specified in the bidding documents
To be submitted by hand, mail or by courier
Other method of submission (where prescribed)
E.g. facsimile

## Slide 18: Withdrawal, modification & Substitution of bids
A bidder may modify, substitute, or withdraw its bid after submission, where the written notice of the modification, substitution or withdrawal is received by the public entity before the deadline for the submission of bids (Sec. 48)

## Slide 19: Receipt and custody of bids
Bids must be deposited into a secure bid box after signing the in-coming bid register, before the closing date and time
Bids must remain unopened until deadline for submission
Late bids shall be returned unopened to the bidder.

## Slide 20: Bid Opening
Every bid shall be opened at the time and place indicated in the bidding documents (Sec. 51)
The time of bid opening shall coincide with the deadline for the submission of bids, or follow immediately thereafter, if this is necessary for logistic reasons.
Every bidder or his representative shall be authorized to attend the bid opening

## Slide 21: Bid Opening
During the Bid Opening, the presence or absence of mandatory documents will be read out and recorded. e.g. Business Registration Certificate, Good Standing Tax Certificate, Good Standing Social Security Certificate and Affirmative Action Compliance Certificate
All amendments and clarifications issued and received by bidders must be acknowledged and form part of the final bid submission;

## Slide 22: Bid Opening
Copy of the opening record shall be made available to all bidder
No decision regarding the disqualification or rejection of a bid shall be taken or announced at the bid opening session

## Slide 23: Evaluation of Bids
Set up bid evaluation committee comprising of qualified evaluators within 5days the deadline for submission (Sec. 52 & Reg. 7)
Ad-Evaluation committee must comprise 3 – 7 members, of which one must be appointed as chairperson
May seek clarification, but may not ask nor permit any bidder to change their prices or substance of its bids

## Slide 24: Evaluation of Bids
Evaluation must be done in accordance to the criteria specified the bidding documents
Evaluation must be concluded in 14 days from the closing date. If extended, no more then 30 days after the closing date
Correct arithmetical error and notify the bidder
Where there is a discrepancy between figures and words, the amount in words shall prevail, and the mistake shall be corrected and the bidder notified

## Slide 25: Evaluation of Bids
Bid evaluation committee must prepare evaluation report detailing the evaluation of bids and how the lowest evaluated bidder was identified
Where the Board or Procurement Committee does not agree with the evaluation report, they should request the BEC to review evaluation process

## Slide 26: Post-qualification
Post-award requirement, toward the lowest evaluated substantially responsive bidder shall be checked against the criteria specified in the bidding documents (Sec. 53)
Where the bid fails to conform to those criteria, the bid shall be rejected and the same check shall be applied to the next ranked bid

## Slide 27: 26. Cancellation of Bidding Process
The Board or a public entity may, at any time prior to the acceptance of a bid, reject all bids or cancel the bidding process, if – (Sec. 54)
all the bids are non-responsive;
the lowest evaluated bid is substantially above the applicable cost estimate;
the goods or services are no longer required;
it has been established that there has been collusion among the bidders as contemplated in subsection (5);

## Slide 28: 27. Cancellation of Bidding Process
The Board or a public entity may, at any time prior to the acceptance of a bid, reject all bids or cancel the bidding process, if -
an irregularity that warrants the cancelation of the bidding process occurred;
it is not economically viable to proceed with the bid; or
does not create or achieve the expected outcome.

## Slide 29: 28. Cancellation of Bidding Process
The Board or a public entity must give a written notice of the rejection of all bids or cancellation of the bidding process to all bidders that submitted bids.
The Board or a public entity may not invite a re-bid for the procurement on the same specifications and contract conditions, if the rejection of all bids or cancellation of bidding process is made on a ground specified in subsection (1)(c), (f) or (g).

## Slide 30: Award
Procurement Committee recommend and Accounting officer approve
A public entity shall publish a notice of selection for award with the executive summary of the bid evaluation report on its website – (Sec 55 (4) & Reg. 38 (1))
the absence of an application for review by bidders within 7days, the Accounting Officer must award the contract to the successful bidder
A procurement contract shall be awarded to the bidder having submitted the lowest evaluated substantially responsive bid

## Slide 31: Award
No negotiation except in special circumstances as may be determined by the Minister
A successful bidder may be asked to submit a performance security (if requested in the bidding document) and sign a contract within 30 days

## Slide 32: Award
If the successful bidder fails to sign a contract or to furnish a performance security, if required, within 30 days, the public entity shall select the next qualifying bidder
The notice of award must include, the procurement subject matter, the name and address of successful bidder and the contract price. (Sec. 55 (8) & Reg. 39)

## Slide 33: Contract management
Monitor the performance
Receive invoices
Facilitate the payment

## Slide 34
Thank You